## Forecast Analysis
Category | Equipment | Total Duration for Extra Units (Days) | Total Duration for Extra Unit (Months) | Required | Owned | Need | Cost of Each Unit | Supplier | Total Cost to Buy | Cost to Hire Each Unit (Monthly) | Supplier | Total Cost to Hire | BUY/HIRE | First Additional Required | Note
Building | Tally Hut | 500 | 11 | 9 | 2 | 7 | 2600 | SEA Containers | 18200 | 590 | SEA Containers | 6490 | HIRE: 7 | Miranda: 07/02/22 | Container can be turned into a hut
| Turnstile | 150 | 5 | 9 | 8 | 1 | 12267 | ROTECH GROUPATF | 12267 | 1022.25 | *From Asset | 5111.25 | HIRE: 1 | Lyon: 09/01/23 | Can possibly be reused
Cage | 4 man cage | 0 | 0 | 4 | 4 | 0 | 6155 | East West Engineering | HAVE ENOUGH
| Open cage | 185 | 6.1667 | 4 | 3 | 1 | 11153 | Safesmart | 11153 | 622.58 | Kennards hire | 3839.2433 | HIRE: 1 | Lyon: 09/01/23 | Not on asset list
| Rescue Cage | 185 | 6.1667 | 4 | 3 | 1 | 3166 | East West Engineering | 3166 | 263.8333 | *From Asset | 1626.9722 | BUY: 1 | Lyon: 09/01/23 | Hire difficult to find
| Material Cage | 185 | 6.1667 | 4 | 3 | 1 | 3126 | Safesmart | 3126 | 3480 | Kennards hire | 21460 | BUY: 1 | Lyon: 09/01/23 | Only one on asset list: Conquip Material Cage
Compressor | Compressor - 200CFM | 885 | 29.5 | 4 | 1 | 3 | 36800 | Ash Air | 110400 | 2313.5 | Hirepool | 68248.25 | HIRE: 3 | Mt Albert: 20/06/22 | CP ELECTRIC CPD 100/8
Container | Tool | 185 | 6.1667 | 4 | 3 | 1 | 3400 | Royal Wolf | 3400 | 590 | SEA Containers | 3638.3333 | BUY: 1 | Lyon: 09/01/23
| Haz | 185 | 6.1667 | 4 | 3 | 1 | 9700 | Addis | 9700 | 390 | SEA Containers | 2405 | HIRE: 1 | Lyon: 09/01/23
| Rig | 185 | 6.1667 | 4 | 3 | 1 | 3400 | Royal Wolf | 3400 | 283.3333 | *From Asset | 1747.2222 | HIRE: 1 | Lyon: 09/01/23
Earthmoving | Digger Telescopic (38T) | 40 | 1.3333 | 2 | 1 | 1 | 530000 | Porters Equipment | 530000 | 8647.9 | Porter Hire | 11530.5333 | HIRE: 1 | Haverstock: 19/09/22 | Hyundai R380LC
| Surface Digger 14T | 185 | 6.1667 | 4 | 1 | 3 | 174200 | Porters Equipment | 522600 | 4921 | Hirepool | 30346.1667 | HIRE: 3 | Miranda: 07/02/22 | Hyundai R140LC-9, Can use UG Digger 14T
| UG Diggger 5.5T | 0 | 0 | 1 | 1 | 0 | 123700 | Porters Equipment | HAVE ENOUGH | [5 empty] | AX55UC-6A
| UG Digger 8T | 325 | 10.8333 | 3 | 1 | 2 | 159350 | Porters Equipment | 318700 | Not on Hire |  |  | BUY: 2 | Rawalpindi: 01/08/22 | Hyundai R80LC-9
| UG Digger 14T | 180 | 6 | 3 | 2 | 1 | 208500 | Porters Equipment | 208500 | Not on Hire |  |  | BUY: 1 | May Rd A: 14/02/22 | Hyundai R145CRD-9, Hyundai HX145CR
| UG Digger 23T | 0 | 0 | 1 | 1 | 0 | 242600 | Porters Equipment | HAVE ENOUGH | [5 empty] | Hyundai R235
| Digger Breaker 8T | 325 | 10.8333 | 3 | 1 | 2 | 15180 | Porters Equipment | 30360 | 4140 | Hirepool | 44850 | BUY: 2 | Mt Albert: 20/06/22
| Digger Breaker 14T | 180 | 6 | 3 | 1 | 2 | 24200 | Porters Equipment | 48400 | 4470 | Hirepool | 26820 | HIRE: 2 | May Rd B: 13/12/21 | FX175
| Digger Breaker 23T | 0 | 0 | 1 | 1 | 0 | 242600 | Porters Equipment | HAVE ENOUGH
| Digger Brush 8T | 150 | 5 | 3 | 2 | 1 | 7260 | Boss Attachment | 7260 | 605 | *From Asset | 3025 | HIRE: 1 | Mt Albert: 20/06/22 | RB80 Sweeper
| Digger Brush 14T | 70 | 2.3333 | 3 | 2 | 1 | 7260 | Boss Attachment | 7260 | 605 | *From Asset | 1411.6667 | HIRE: 1 | May Rd B: 13/12/21 | RB80 Sweeper
| Digger Drill Attachment 8T | 325 | 10.8333 | 3 | 1 | 2 | 64900 | HMI NZ LTD | 129800 | 5408.3333 | *From Asset | 58590.2778 | HIRE: 2 | Mt Albert: 20/06/22 | TEI Hydraulic Drill Attachment | Description | Weekyl Rate
| Digger Drill Attachment 14T | 180 | 6 | 3 | 1 | 2 | 64900 | HMI NZ LTD | 129800 | 5408.3333 | *From Asset | 32450 | HIRE: 2 | Miranda: 07/02/22 | TEI Hydraulic Drill Attachment | 50t Crawler | 5150
| Digger Milling Head 8T | 325 | 10.8333 | 3 | 1 | 2 | 37397 | Boss Attachment | 74794 | 3116.4167 | *From Asset | 33761.1806 | HIRE: 2 | Rawalpindi: 01/08/22 | AQ1 | 80t Crawler | 6250
| Digger Milling Head 14T | 70 | 2.3333 | 3 | 2 | 1 | 41136.7 | Boss Attachment | 41136.7 | 3428.0583 | *From Asset | 7998.8028 | HIRE: 1 | May Rd B: 13/12/21 | AQ1, AQ2 | 100t Crawler | 6850
Electrical | Sub Pump | 0 | 0 | 10 | 10 | HAVE ENOUGH | [9 empty] | 120t Crawler | 7150
| Generator Backup (250kVA) | 0 | 0 | 1 | 2 | HAVE ENOUGH | [8 empty] | CAT DE275E0 | 150t Crawler | 8350
| Generator Backup (300kVA) | 1365 | 45.5 | 4 | 0 | 4 | Contacted Supplier | Terra CAT | - | 6000 | GRS | 273000 | HIRE: 4 | Miranda: 07/02/22 |  | 200t Crawler | 9000
| Switchboard | 411 | 13.7 | 4 | WITH GENERATOR | [10 empty] | 250-280t Crawler | 10000
Grout | Grout Pump S5 EVTM | 955 | 31.8333 | 4 | 1 | 3 | 22955 | Concrete Pumping Equp | 68865 | 1912.9167 | *From Asset | 60894.5139 | HIRE: 3 | May Rd A: 14/02/22 | S5 EVTM
Lifting | 100t Crawler Crane | 570 | 19 | 4 | 0 | 4 | Not Buying |  |  | 6850 | Smith Crane | 130150 | HIRE: 4 | Rawalpindi: 01/08/22 | Smith Crane Rates: $6,850/month
| 120t Crawler Crane | 295 | 9.8333 | 1 | 0 | 1 | Not Buying |  |  | 7150 | Smith Crane | 70308.3333 | HIRE: 1 | May Rd A: 14/02/22 | Smith Crane Rates: $7,150/month
| 160t Crawler Crane | 500 | 16.6667 | 2 | 0 | 2 | Not Buying |  |  | 8350 | Smith Crane | 139166.6667 | HIRE: 2 | Miranda: 07/02/22 | Smith Crane Rates: $8,350/month
Shotcrete | Shotcrete Aliva 272 | 110 | 3.6667 | 2 | 1 | 1 | 159950 | Concrete Pumping Equp | 159950 | 12303.85 | *From Asset | 45114.1167 | HIRE: 1 | May Rd A: 14/02/22 | Aliva 272
Skip | Skip (3m3) | 865 | 28.8333 | 3 | 0 | 3 | 9500 | Powerpac | 28500 | 4500 | Powerpac | 129750 | BUY: 3 | May Rd A: 14/02/22
| Skip (4m3) | 500 | 16.6667 | 2 | 0 | 2 | 12500 | Powerpac | 25000 | 5400 | Powerpac | 90000 | BUY: 2 | Miranda: 07/02/22
Ventilation | Ventilation Fan | 0 | 0 | 4 | 10 | HAVE ENOUGH
| Gasguard | 500 | 16.6667 | 4 | 1 | 3 | 7940.94 | - | 23822.82 | Not on Hire |  |  | BUY: 3 | Miranda: 07/02/22
Water Treatment | WTP Plant | 0 | 0 | 1 | 3 | HAVE ENOUGH | [8 empty] | CONDOR
[11 empty] | *From Asset | Rate = Asset Price/12

## Total Duration Needed for Extra
Category | Equipment | Location | Duration (Days) | Total Duration (Months) | Unit Required | Unit Owned | Unit Needed | Total Duration Needed | Duration (Months) Needed
Building | Tally Hut | May Rd A | 110 | Unit 1 | 4 | 2 | 2 | 500 | 16.6667
|  | May Rd B | 280 | Unit 2
|  | Miranda | 70 | Unit 3
|  | Haverstock | 175 | Unit 2
|  | Mt Albert | 125 | Unit 3
|  | Norgrove | 120 | Unit 3
|  | Rawalpindi | 150 | Unit 1
|  | Lyon | 185 | Unit 4
|  | Western Springs | 150 | Unit 1
| Turnstile | May Rd A | 110 | Unit 1 | 9 | 8 | 1 | 150 | 5
|  | May Rd B | 280 | Unit 2
|  | Miranda | 70 | Unit 3
|  | Haverstock | 175 | Unit 4
|  | Mt Albert | 125 | Unit 5
|  | Norgrove | 120 | Unit 6
|  | Rawalpindi | 150 | Unit 7
|  | Lyon | 185 | Unit 8
|  | Western Springs | 150 | Unit 9
Cage | 4 man cage | May Rd A | 110 | Unit 1 | 4 | 4 | 0 | 0 | 0
|  | May Rd B | 280 | Unit 3
|  | Miranda | 70 | Unit 2
|  | Haverstock | 175 | Unit 3
|  | Mt Albert | 125 | Unit 2
|  | Norgrove | 120 | Unit 2
|  | Rawalpindi | 150 | Unit 1
|  | Lyon | 185 | Unit 4
|  | Western Springs | 150 | Unit 1
| Open cage | May Rd A | 110 | Unit 1 | 4 | 3 | 1 | 185 | 6.1667
|  | May Rd B | 280 | Unit 3
|  | Miranda | 70 | Unit 2
|  | Haverstock | 175 | Unit 3
|  | Mt Albert | 125 | Unit 2
|  | Norgrove | 120 | Unit 2
|  | Rawalpindi | 150 | Unit 1
|  | Lyon | 185 | Unit 4
|  | Western Springs | 150 | Unit 1
| Rescue Cage | May Rd A | 110 | Unit 1 | 4 | 3 | 1 | 185 | 6.1667
|  | May Rd B | 280 | Unit 3
|  | Miranda | 70 | Unit 2
|  | Haverstock | 175 | Unit 3
|  | Mt Albert | 125 | Unit 2
|  | Norgrove | 120 | Unit 2
|  | Rawalpindi | 150 | Unit 1
|  | Lyon | 185 | Unit 4
|  | Western Springs | 150 | Unit 1
| Material Cage | May Rd A | 110 | Unit 1 | 4 | 3 | 1 | 185 | 6.1667
|  | May Rd B | 280 | Unit 3
|  | Miranda | 70 | Unit 2
|  | Haverstock | 175 | Unit 3
|  | Mt Albert | 125 | Unit 2
|  | Norgrove | 120 | Unit 2
|  | Rawalpindi | 150 | Unit 1
|  | Lyon | 185 | Unit 4
|  | Western Springs | 150 | Unit 1
Compressor | Compressor - 200CFM | May Rd A | 110 | Unit 1 | 4 | 1 | 3 | 885 | 29.5
|  | May Rd B | 280 | Unit 2
|  | Haverstock | 175 | Unit 2
|  | Mt Albert | 125 | Unit 3
|  | Norgrove | 120 | Unit 3
|  | Rawalpindi | 150 | Unit 1
|  | Lyon | 185 | Unit 4
|  | Western Springs | 150 | Unit 1
Container | Tool | May Rd A | 110 | Unit 1 | 4 | 3 | 1 | 185 | 6.1667
|  | May Rd B | 280 | Unit 3
|  | Miranda | 70 | Unit 2
|  | Haverstock | 175 | Unit 3
|  | Mt Albert | 125 | Unit 2
|  | Norgrove | 120 | Unit 2
|  | Rawalpindi | 150 | Unit 1
|  | Lyon | 185 | Unit 4
|  | Western Springs | 150 | Unit 1
| Haz | May Rd A | 110 | Unit 1 | 4 | 3 | 1 | 185 | 6.1667
|  | May Rd B | 280 | Unit 3
|  | Miranda | 70 | Unit 2
|  | Haverstock | 175 | Unit 3
|  | Mt Albert | 125 | Unit 2
|  | Norgrove | 120 | Unit 2
|  | Rawalpindi | 150 | Unit 1
|  | Lyon | 185 | Unit 4
|  | Western Springs | 150 | Unit 1
| Rig | May Rd A | 110 | Unit 1 | 4 | 3 | 1 | 185 | 6.1667
|  | May Rd B | 280 | Unit 3
|  | Miranda | 70 | Unit 2
|  | Haverstock | 175 | Unit 3
|  | Mt Albert | 125 | Unit 2
|  | Norgrove | 120 | Unit 2
|  | Rawalpindi | 150 | Unit 1
|  | Lyon | 185 | Unit 4
|  | Western Springs | 150 | Unit 1
Earthmoving | Digger Telescopic (38T) | Miranda | 70 | Unit 1 | 2 | 1 | 1 | 40 | 13.3333
|  | Haverstock | 40 | Unit 2
|  | Norgrove | 120 | Unit 1
|  | Rawalpindi | 50 | Unit 1
| Surface Digger 14T | May Rd A | 110 | Unit 1 | 4 | 1 | 3 | 185 | 61.6667
|  | May Rd B | 60 | Unit 2
|  | Miranda | 280 | Unit 3
|  | Haverstock | 70 | Unit 2
|  | Mt Albert | 175 | Unit 3
|  | Norgrove | 125 | Unit 3
|  | Rawalpindi | 150 | Unit 1
|  | Lyon | 185 | Unit 4
|  | Western Springs | 150 | Unit 1
| UG Diggger 5.5T | Norgrove | 120 | Unit 1 | 1 | 1 | 0 | 0 | 0
| UG Digger 8T | Haverstock | 175 | Unit 1 | 3 | 1 | 2 | 325 | 10.8333
|  | Mt Albert | 125 | Unit 2
|  | Rawalpindi | 150 | Unit 3
|  | Lyon | 185 | Unit 2
| UG Digger 14T | May Rd A | 110 | Unit 1 | 3 | 1 | 2 | 180 | 6
|  | May Rd B | 185 | Unit 2
|  | Miranda | 70 | Unit 3
|  | Western Springs | 150 | Unit 2
| UG Digger 23T | May Rd B | 280 | Unit 1 | 1 | 1 | 0 | 0 | 0
|  | Western Springs | 150 | Unit 1
| Digger Breaker 8T | Haverstock | 175 | Unit 1 | 3 | 1 | 2 | 325 | 10.8333
|  | Mt Albert | 125 | Unit 2
|  | Rawalpindi | 150 | Unit 3
|  | Lyon | 185 | Unit 2
| Digger Breaker 14T | May Rd A | 110 | Unit 1 | 3 | 1 | 2 | 180 | 6
|  | May Rd B | 185 | Unit 2
|  | Miranda | 70 | Unit 3
|  | Western Springs | 150 | Unit 2
| Digger Breaker 23T | May Rd B | 280 | Unit 1 | 1 | 1 | 0 | 0 | 0
|  | Western Springs | 150 | Unit 1
| Digger Brush 8T | Haverstock | 175 | Unit 1 | 3 | 2 | 1 | 150 | 5
|  | Mt Albert | 125 | Unit 2
|  | Rawalpindi | 150 | Unit 3
|  | Lyon | 185 | Unit 2
| Digger Brush 14T | May Rd A | 110 | Unit 1 | 3 | 2 | 1 | 70 | 2.3333
|  | May Rd B | 185 | Unit 2
|  | Miranda | 70 | Unit 3
|  | Western Springs | 150 | Unit 2
| Digger Drill Attachment 8T | Haverstock | 175 | Unit 1 | 3 | 1 | 2 | 325 | 10.8333
|  | Mt Albert | 125 | Unit 2
|  | Rawalpindi | 150 | Unit 3
|  | Lyon | 185 | Unit 2
| Digger Drill Attachment 14T | May Rd A | 110 | Unit 1 | 3 | 1 | 2 | 180 | 6
|  | May Rd B | 185 | Unit 2
|  | Miranda | 70 | Unit 3
|  | Western Springs | 150 | Unit 2
| Digger Milling Head 8T | Haverstock | 175 | Unit 1 | 3 | 1 | 2 | 325 | 10.8333
|  | Mt Albert | 125 | Unit 2
|  | Rawalpindi | 150 | Unit 3
|  | Lyon | 185 | Unit 2
| Digger Milling Head 14T | May Rd A | 110 | Unit 1 | 3 | 2 | 1 | 70 | 2.3333
|  | May Rd B | 185 | Unit 2
|  | Miranda | 70 | Unit 3
|  | Western Springs | 150 | Unit 2
Electrical | Generator Backup (300kVA) | May Rd A | 110 | Unit 1 | 4 | 0 | 4 | 1365 | 45.5
|  | May Rd B | 280 | Unit 2
|  | Miranda | 70 | Unit 3
|  | Haverstock | 175 | Unit 2
|  | Mt Albert | 125 | Unit 3
|  | Norgrove | 120 | Unit 3
|  | Rawalpindi | 150 | Unit 1
|  | Lyon | 185 | Unit 4
|  | Western Springs | 150 | Unit 1
Grout | Grout Pump S5 EVTM | May Rd A | 110 | Unit 1 | 4 | 1 | 3 | 955 | 31.8333
|  | May Rd B | 280 | Unit 2
|  | Miranda | 70 | Unit 3
|  | Haverstock | 175 | Unit 2
|  | Mt Albert | 125 | Unit 3
|  | Norgrove | 120 | Unit 3
|  | Rawalpindi | 150 | Unit 1
|  | Lyon | 185 | Unit 4
|  | Western Springs | 150 | Unit 1
Lifting | 100t Crawler Crane | Haverstock | 175 | Unit 1 | 3 | 0 | 3 | 570 | 19
|  | Mt Albert | 125 | Unit 2
|  | Norgrove | 120 | Unit 2
|  | Rawalpindi | 150 | Unit 3
| 120t Crawler Crane | May Rd A | 110 | Unit 1 | 1 | 0 | 1 | 295 | 9.8333
|  | Lyon | 185 | Unit 1
| 160t Crawler Crane | May Rd B | 280 | Unit 1 | 2 | 0 | 2 | 500 | 16.6667
|  | Miranda | 70 | Unit 2
|  | Western Springs | 150 | Unit 2
Shotcrete | Shotcrete Aliva 272 | May Rd A | 110 | Unit 1 | 2 | 1 | 1 | 110 | 3.6667
|  | May Rd B | 280 | Unit 2
|  | Lyon | 185 | Unit 2
Skip | Skip (3m3) | May Rd A | 110 | Unit 1 | 4 | 0 | 4 | 865 | 28.8333
|  | Haverstock | 175 | Unit 2
|  | Mt Albert | 125 | Unit 3
|  | Norgrove | 120 | Unit 3
|  | Rawalpindi | 150 | Unit 1
|  | Lyon | 185 | Unit 4
| Skip (4m3) | May Rd B | 280 | Unit 1 | 2 | 0 | 2 | 500 | 16.6667
|  | Miranda | 70 | Unit 2
|  | Western Springs | 150 | Unit 2

## Crane
Location | UG Digger | Crane Requirement | Unit | Transfer To | Duration (days) | Duration (week) | Cost
May Rd A | 14T | 120T | Unit 1 |  | 110 | 22 | 154000
May Rd B | 23T | 160T | Unit 1 |  | 280 | 56 | 462000
Miranda | 14T | 160T | Unit 2 | --> Western Springs | 70 | 14 | 115500
Haverstock | 8T | 100T | Unit 2 |  | 175 | 35 | 236250
Mt Albert | 8T | 100T | Unit 1 | --> Norgrove | 125 | 25 | 168750
Norgrove | 5.5T | 100T | Unit 1 |  | 120 | 24 | 162000
Rawalpindi | 8T | 100T | Unit 3 |  | 150 | 30 | 202500
Lyon | 8T | 100T | Unit 4 |  | 185 | 37 | 249750
Western Springs | 23T | 160T | Unit 2 |  | 150 | 30 | 247500
[6 empty] | Total | 1998250
[6 empty] | Transfer Fee | 22000
Description | Weekly Rate |  | Units | Needed |  |  | 2020250
50t Crawler | 5000 |  | 100T | 4
80t Crawler | 6000 |  | 120T | 1
100t Crawler | 6750 |  | 160T | 2
120t Crawler | 7000
150t Crawler | 8250
200t Crawler | 8750
250-280t Crawler | 9000