## 2021-2023
|  |  |  | Jan W2 | Jan W3 | Jan W4 | Jan W5 | Feb W6 | Feb W7 | Feb W8 | Feb W9 | Mar W10 | Mar W11 | Mar W12 | Mar W13 | Mar W14 | Apr W15 | Apr W16 | Apr W17 | Apr W18 | May W19 | May W20 | May W21 | May W22 | May W23 | Jun W24 | Jun W25 | Jun W26 | Jun W27 | Jul W28 | Jul W29 | Jul W30 | Jul W31 | Aug W32 | Aug W33 | Aug W34 | Aug W35 | Aug W36 | Sep W37 | Sep W38 | Sep W39 | Sep W40 | Oct W41 | Oct W42 | Oct W43 | Oct W44 | Nov W45 | Nov W46 | Nov W47 | Nov W48 | Nov W49 | Dec W50 | Dec W51 | Dec W52 | Dec W53 | Jan W2 | Jan W3 | Jan W4 | Jan W5 | Jan W6 | Feb W7 | Feb W8 | Feb W9 | Feb W10 | Mar W11 | Mar W12 | Mar W13 | Mar W14 | Apr W15 | Apr W16 | Apr W17 | Apr W18 | May W19 | May W20 | May W21 | May W22 | May W23 | Jun W24 | Jun W25 | Jun W26 | Jun W27 | Jul W28 | Jul W29 | Jul W30 | Jul W31 | Aug W32 | Aug W33 | Aug W34 | Aug W35 | Aug W36 | Sep W37 | Sep W38 | Sep W39 | Sep W40 | Oct W41 | Oct W42 | Oct W43 | Oct W44 | Oct W45 | Nov W46 | Nov W47 | Nov W48 | Nov W49 | Dec W50 | Dec W51 | Dec W52 | Dec W53 | Jan W1 | Jan W2 | Jan W3 | Jan W4 | Jan W5 | Feb W6 | Feb W7 | Feb W8 | Feb W9 | Mar W10 | Mar W11 | Mar W12 | Mar W13 | Apr W14 | Apr W15 | Apr W16 | Apr W17 | May W18 | May W19 | May W20 | May W21 | May W22 | Jun W23 | Jun W24 | Jun W25 | Jun W26 | Jul W27 | Jul W28 | Jul W29 | Jul W30 | Jul W31 | Aug W32 | Aug W33 | Aug W34 | Aug W35 | Sep W36 | Sep W37 | Sep W38 | Sep W39 | Oct W40 | Oct W41 | Oct W42 | Oct W43 | Oct W44 | Nov W45 | Nov W46 | Nov W47 | Nov W48 | Dec W49 | Dec W50 | Dec W51 | Dec W52
Shaft & Microtunnels - Plant & Equipment Requirements | time axis 2021-01-04 to 2023-12-25
Sort No. | Location | Weeks Hire | Item
0
| COMBINED RESOURCES | 228 | compressor - 200CFM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 2 | 2 | 3 | 3 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| COMBINED RESOURCES | 216 | Putzmeister S5 Ev Grout Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 2 | 2 | 3 | 3 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| COMBINED RESOURCES | 98 | skip - 4m3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| COMBINED RESOURCES | 98 | cage - open | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| COMBINED RESOURCES | 267 | cage - materials | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 2 | 2 | 3 | 3 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| COMBINED RESOURCES | 279 | cage - rescue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 2 | 2 | 3 | 3 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| COMBINED RESOURCES | 279 | cage - 4 man | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 2 | 2 | 3 | 3 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| COMBINED RESOURCES | 279 | switchboard | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 2 | 2 | 3 | 3 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 |  |  | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| COMBINED RESOURCES | 267 | Tally hut | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 2 | 2 | 3 | 3 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 |  |  | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| COMBINED RESOURCES | 279 | container - haz. goods | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 2 | 2 | 3 | 3 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 |  |  | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| COMBINED RESOURCES | 279 | container - rigging | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 2 | 2 | 3 | 3 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 |  |  | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| COMBINED RESOURCES | 279 | container - tool | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 2 | 2 | 3 | 3 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 |  |  | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| COMBINED RESOURCES | 267 | Full height Turnstile | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 2 | 2 | 3 | 3 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 |  |  | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| COMBINED RESOURCES | 279 | gasguard | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 2 | 2 | 3 | 3 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 |  |  | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| COMBINED RESOURCES | 382 | Submersible pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 |  |  | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 6 | 6 | 6 | 6 | 6 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
| COMBINED RESOURCES | 191 | ventilation fan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 |  |  | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| COMBINED RESOURCES | 267 | generator - backup - 300kVA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 2 | 2 | 3 | 3 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 |  |  | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| COMBINED RESOURCES | 279 | Surface digger (14t) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 2 | 2 | 3 | 3 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 |  |  | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| COMBINED RESOURCES | 132 | digger breaker (14t) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| COMBINED RESOURCES | 132 | digger milling head (14t) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| COMBINED RESOURCES | 44 | Digger attachement brush (14t) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| COMBINED RESOURCES | 118 | digger drill attachment (14t) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| COMBINED RESOURCES | 113 | UG digger (14t) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| COMBINED RESOURCES | 84 | Digger breaker (23t) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| COMBINED RESOURCES | 84 | UG digger (23t) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| COMBINED RESOURCES | 189 | crawler crane | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 |  |  | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| COMBINED RESOURCES | 88 | shotcrete - Aliva 272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| COMBINED RESOURCES | 144 | skip - 3m3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| COMBINED RESOURCES | 159 | cage - open | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 |  |  | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| COMBINED RESOURCES | 123 | digger milling head (8t) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 |  |  | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| COMBINED RESOURCES | 123 | Digger attachement brush (8t) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 |  |  | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| COMBINED RESOURCES | 123 | digger drill attachment (8t) | [30 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 |  |  | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| COMBINED RESOURCES | 123 | Digger breaker (8t) | [30 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 |  |  | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| COMBINED RESOURCES | 123 | UG digger (8t) | [30 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| COMBINED RESOURCES | 56 | 38t digger - telescopic | [30 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| COMBINED RESOURCES | 24 | digger milling head (5.5t) | [30 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| COMBINED RESOURCES | 24 | Digger attachement brush (5.5t) | [30 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| COMBINED RESOURCES | 24 | digger drill attachment (5.5t) | [30 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| COMBINED RESOURCES | 24 | Digger breaker (5.5t) | [30 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| COMBINED RESOURCES | 24 | UG digger (5.5t) | [30 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| COMBINED RESOURCES | 68 | 160t crawler crane | [30 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| COMBINED RESOURCES | 152 | sub. Pump - 15litre/sec 78m head | [30 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| COMBINED RESOURCES | 88 | Fan - Zitron gEL9-37/2 (15m3/s) | [30 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| COMBINED RESOURCES | 54 | Digger attachement brust (14t) | [30 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| COMBINED RESOURCES | 12 | cage - tool | [30 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| COMBINED RESOURCES | 12 | generator - backup - 250kVA | [30 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| COMBINED RESOURCES | 12 | water treatment device | [30 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| COMBINED RESOURCES | 24 | sub. Pump - 3.5litre/sec 25m head | [30 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| COMBINED RESOURCES | 12 | digger brush (14t) | [30 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| COMBINED RESOURCES | 12 | digger - telescopic | [30 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| COMBINED RESOURCES | 22 | 120t crawler crane | [30 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| COMBINED RESOURCES | 0 | #N/A | [30 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[34 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DSCIN004 May Road A START: 3/3/22 DURATION:18WKS
| DSCIN004 May Road A |  | 120t crawler crane | bar: 2022-02-14 to 2022-07-11
| DSCIN004 May Road A | TBC | UG digger (14t) | bar: 2022-02-14 to 2022-07-11
| DSCIN004 May Road A |  | digger drill attachment (14t) | bar: 2022-02-14 to 2022-07-11
| DSCIN004 May Road A |  | digger milling head (14t) | bar: 2022-02-14 to 2022-07-11
| DSCIN004 May Road A |  | digger breaker (14t) | bar: 2022-02-14 to 2022-07-11
| DSCIN004 May Road A |  | Surface digger (14t) | bar: 2022-02-14 to 2022-07-11
| DSCIN004 May Road A | Shared between Shaft B | generator - backup - 300kVA | bar: 2022-02-14 to 2022-07-11
| DSCIN004 May Road A |  | Fan - Zitron gEL9-37/2 (15m3/s) | bar: 2022-02-14 to 2022-07-11
| DSCIN004 May Road A |  | sub. Pump - 15litre/sec 78m head | 2022-02-14: 2; 2022-02-21: 2; 2022-02-28: 2; 2022-03-07: 2; 2022-03-14: 2; 2022-03-21: 2; 2022-03-28: 2; 2022-04-04: 2; 2022-04-11: 2; 2022-04-18: 2; 2022-04-25: 2; 2022-05-02: 2; 2022-05-09: 2; 2022-05-16: 2; 2022-05-23: 2; 2022-05-30: 2; 2022-06-06: 2; 2022-06-13: 2; 2022-06-20: 2; 2022-06-27: 2; 2022-07-04: 2; 2022-07-11: 2
| DSCIN004 May Road A |  | gasguard | 2021-11-08: 0; 2021-11-15: 0; 2021-11-22: 0; 2021-11-29: 0; 2021-12-06: 0; 2021-12-13: 0; 2022-02-14: 1; 2022-02-21: 1; 2022-02-28: 1; 2022-03-07: 1; 2022-03-14: 1; 2022-03-21: 1; 2022-03-28: 1; 2022-04-04: 1; 2022-04-11: 1; 2022-04-18: 1; 2022-04-25: 1; 2022-05-02: 1; 2022-05-09: 1; 2022-05-16: 1; 2022-05-23: 1; 2022-05-30: 1; 2022-06-06: 1; 2022-06-13: 1; 2022-06-20: 1; 2022-06-27: 1; 2022-07-04: 1; 2022-07-11: 1
| DSCIN004 May Road A |  | Full height Turnstile | bar: 2022-02-14 to 2022-07-11
| DSCIN004 May Road A |  | container - tool | bar: 2022-02-14 to 2022-07-11
| DSCIN004 May Road A |  | container - rigging | bar: 2022-02-14 to 2022-07-11
| DSCIN004 May Road A | 2no at May Road | container - haz. goods | bar: 2022-02-14 to 2022-07-11
| DSCIN004 May Road A |  | Tally hut | bar: 2022-02-14 to 2022-07-11
| DSCIN004 May Road A |  | switchboard | bar: 2022-02-14 to 2022-07-11
| DSCIN004 May Road A |  | cage - 4 man | bar: 2022-02-14 to 2022-07-11
| DSCIN004 May Road A |  | cage - rescue | bar: 2022-02-14 to 2022-07-11
| DSCIN004 May Road A |  | cage - materials | bar: 2022-02-14 to 2022-07-11
| DSCIN004 May Road A | Back up 4m3 required | skip - 3m3 | bar: 2022-02-14 to 2022-07-11
| DSCIN004 May Road A |  | Putzmeister S5 Ev Grout Pump | bar: 2022-02-14 to 2022-07-11
| DSCIN004 May Road A |  | shotcrete - Aliva 272 | bar: 2022-02-14 to 2022-07-11
| DSCIN004 May Road A |  | compressor - 200CFM | bar: 2022-02-14 to 2022-07-11
DSLC002 Dundale Ave START:06/12/21 DURATION:14WKS
| DSLSC002 Dundale Ave |  | crawler crane | bar: 2021-08-02 to 2021-10-18
| DSLSC002 Dundale Ave |  | digger - telescopic | bar: 2021-08-02 to 2021-10-18
| DSLSC002 Dundale Ave |  | UG digger (14t) | bar: 2021-08-02 to 2021-10-18
| DSLSC002 Dundale Ave |  | digger drill attachment (14t) | bar: 2021-08-02 to 2021-10-18
| DSLSC002 Dundale Ave |  | digger brush (14t) | bar: 2021-08-02 to 2021-10-18
| DSLSC002 Dundale Ave |  | digger milling head (14t) | bar: 2021-08-02 to 2021-10-18
| DSLSC002 Dundale Ave |  | digger breaker (14t) | bar: 2021-08-02 to 2021-10-18
| DSLSC002 Dundale Ave |  | Surface digger (14t) | bar: 2021-08-02 to 2021-10-18
| DSLSC002 Dundale Ave |  | Fan - Zitron gEL9-37/2 (15m3/s) | bar: 2021-08-02 to 2021-10-18
| DSLSC002 Dundale Ave |  | sub. Pump - 3.5litre/sec 25m head | bar: 2021-08-02 to 2021-10-18
| DSLSC002 Dundale Ave |  | sub. Pump - 3.5litre/sec 25m head | bar: 2021-08-02 to 2021-10-18
| DSLSC002 Dundale Ave |  | water treatment device | bar: 2021-08-02 to 2021-10-18
| DSLSC002 Dundale Ave |  | generator - backup - 250kVA | bar: 2021-08-02 to 2021-10-18
| DSLSC002 Dundale Ave |  | switchboard | bar: 2021-08-02 to 2021-10-18
| DSLSC002 Dundale Ave |  | container - tool | bar: 2021-08-02 to 2021-10-18
| DSLSC002 Dundale Ave |  | container - rigging | bar: 2021-08-02 to 2021-10-18
| DSLSC002 Dundale Ave |  | container - haz. goods | bar: 2021-08-02 to 2021-10-18
| DSLSC002 Dundale Ave |  | gasguard | bar: 2021-08-02 to 2021-10-18
| DSLSC002 Dundale Ave |  | cage - 4 man | bar: 2021-08-02 to 2021-10-18
| DSLSC002 Dundale Ave |  | cage - rescue | bar: 2021-08-02 to 2021-10-18
| DSLSC002 Dundale Ave |  | cage - tool | bar: 2021-08-02 to 2021-10-18
| DSLSC002 Dundale Ave |  | cage - open | bar: 2021-08-02 to 2021-10-18
| DSLSC002 Dundale Ave |  | skip - 3m3 | bar: 2021-08-02 to 2021-10-18
| DSLSC002 Dundale Ave |  | shotcrete - Aliva 272 | bar: 2021-08-02 to 2021-10-18
| DSLSC002 Dundale Ave |  | compressor - 200CFM | bar: 2021-08-02 to 2021-10-18
DSCIN004 May Road B START:06/12/21 DURATION
| DSCIN004 May Road B |  | 160t crawler crane | bar: 2021-08-02 to 2021-12-13; 2022-01-03 to 2022-08-22
| DSCIN004 May Road B | Excavation in rock | UG digger (23t) | bar: 2021-08-02 to 2021-12-13; 2022-01-03 to 2022-08-22
| DSCIN004 May Road B |  | Digger breaker (23t) | bar: 2021-08-02 to 2021-12-13; 2022-01-03 to 2022-08-22
| DSCIN004 May Road B | Rockbolts and milling | UG digger (14t) | bar: 2021-12-13; 2022-01-03 to 2022-08-22
| DSCIN004 May Road B |  | digger drill attachment (14t) | bar: 2021-08-02 to 2021-12-13; 2022-01-03 to 2022-08-22
| DSCIN004 May Road B |  | Digger attachement brust (14t) | bar: 2021-08-02 to 2021-12-13; 2022-01-03 to 2022-08-22
| DSCIN004 May Road B |  | digger milling head (14t) | bar: 2021-08-02 to 2021-12-13; 2022-01-03 to 2022-08-22
| DSCIN004 May Road B |  | digger breaker (14t) | bar: 2021-08-02 to 2021-12-13; 2022-01-03 to 2022-08-22
| DSCIN004 May Road B |  | Surface digger (14t) | bar: 2021-08-02 to 2021-12-13; 2022-01-03 to 2022-08-22
| DSCIN004 May Road B |  | generator - backup - 300kVA | bar: 2021-08-02 to 2021-12-13; 2022-01-03 to 2022-08-22
| DSCIN004 May Road B |  | Fan - Zitron gEL9-37/2 (15m3/s) | bar: 2021-08-02 to 2021-12-13; 2022-01-03 to 2022-08-22
| DSCIN004 May Road B |  | sub. Pump - 15litre/sec 78m head | 2021-08-02: 2; 2021-08-09: 2; 2021-08-16: 2; 2021-08-23: 2; 2021-08-30: 2; 2021-09-06: 2; 2021-09-13: 2; 2021-09-20: 2; 2021-09-27: 2; 2021-10-04: 2; 2021-10-11: 2; 2021-10-18: 2; 2021-10-25: 2; 2021-11-01: 2; 2021-11-08: 2; 2021-11-15: 2; 2021-11-22: 2; 2021-11-29: 2; 2021-12-06: 2; 2021-12-13: 2; 2022-01-03: 2; 2022-01-10: 2; 2022-01-17: 2; 2022-01-24: 2; 2022-01-31: 2; 2022-02-07: 2; 2022-02-14: 2; 2022-02-21: 2; 2022-02-28: 2; 2022-03-07: 2; 2022-03-14: 2; 2022-03-21: 2; 2022-03-28: 2; 2022-04-04: 2; 2022-04-11: 2; 2022-04-18: 2; 2022-04-25: 2; 2022-05-02: 2; 2022-05-09: 2; 2022-05-16: 2; 2022-05-23: 2; 2022-05-30: 2; 2022-06-06: 2; 2022-06-13: 2; 2022-06-20: 2; 2022-06-27: 2; 2022-07-04: 2; 2022-07-11: 2; 2022-07-18: 2; 2022-07-25: 2; 2022-08-01: 2; 2022-08-08: 2; 2022-08-15: 2; 2022-08-22: 2
| DSCIN004 May Road B |  | gasguard | bar: 2021-08-02 to 2021-12-13; 2022-01-03 to 2022-08-22
| DSCIN004 May Road B |  | Full height Turnstile | bar: 2021-08-02 to 2021-12-13; 2022-01-03 to 2022-08-22
| DSCIN004 May Road B |  | container - tool | bar: 2021-08-02 to 2021-12-13; 2022-01-03 to 2022-08-22
| DSCIN004 May Road B |  | container - rigging | bar: 2021-08-02 to 2021-12-13; 2022-01-03 to 2022-08-22
| DSCIN004 May Road B |  | container - haz. goods | bar: 2021-08-02 to 2021-12-13; 2022-01-03 to 2022-08-22
| DSCIN004 May Road B |  | Tally hut | bar: 2021-08-02 to 2021-12-13; 2022-01-03 to 2022-08-22
| DSCIN004 May Road B |  | switchboard | bar: 2021-08-02 to 2021-12-13; 2022-01-03 to 2022-08-22
| DSCIN004 May Road B |  | cage - 4 man | bar: 2021-08-02 to 2021-12-13; 2022-01-03 to 2022-08-22
| DSCIN004 May Road B |  | cage - rescue | bar: 2021-08-02 to 2021-12-13; 2022-01-03 to 2022-08-22
| DSCIN004 May Road B |  | cage - materials | bar: 2021-08-02 to 2021-12-13; 2022-01-03 to 2022-08-22
| DSCIN004 May Road B |  | cage - open | bar: 2021-08-02 to 2021-12-13; 2022-01-03 to 2022-08-22
| DSCIN004 May Road B |  | skip - 4m3 | bar: 2021-08-02 to 2021-12-13; 2022-01-03 to 2022-08-22
| DSCIN004 May Road B |  | Putzmeister S5 Ev Grout Pump | bar: 2021-08-02 to 2021-12-13; 2022-01-03 to 2022-08-22
| DSCIN004 May Road B |  | shotcrete - Aliva 272 | bar: 2021-08-02 to 2021-12-13; 2022-01-03 to 2022-08-22
| DSCIN004 May Road B |  | compressor - 200CFM | bar: 2021-08-02 to 2021-12-13; 2022-01-03 to 2022-08-22
DSLSC004 Miranda Res START:23/02/22 DURATION:10WKS
| DSLSC004 Miranda Res |  | 160t crawler crane | bar: 2022-02-07 to 2022-05-09
| DSLSC004 Miranda Res |  | 38t digger - telescopic | bar: 2022-02-07 to 2022-05-09
| DSLSC004 Miranda Res |  | UG digger (14t) | bar: 2022-02-07 to 2022-05-09
| DSLSC004 Miranda Res |  | Digger attachement brush (14t) | bar: 2022-02-07 to 2022-05-09
| DSLSC004 Miranda Res |  | digger milling head (14t) | bar: 2022-02-07 to 2022-05-09
| DSLSC004 Miranda Res |  | digger breaker (14t) | bar: 2022-02-07 to 2022-05-09
| DSLSC004 Miranda Res |  | Surface digger (14t) | bar: 2022-02-07 to 2022-05-09
| DSLSC004 Miranda Res |  | generator - backup - 300kVA | bar: 2022-02-07 to 2022-05-09
| DSLSC004 Miranda Res |  | ventilation fan | bar: 2022-02-07 to 2022-05-09
| DSLSC004 Miranda Res |  | Submersible pump | 2022-02-07: 2; 2022-02-14: 2; 2022-02-21: 2; 2022-02-28: 2; 2022-03-07: 2; 2022-03-14: 2; 2022-03-21: 2; 2022-03-28: 2; 2022-04-04: 2; 2022-04-11: 2; 2022-04-18: 2; 2022-04-25: 2; 2022-05-02: 2; 2022-05-09: 2
| DSLSC004 Miranda Res |  | gasguard | bar: 2022-02-07 to 2022-05-09
| DSLSC004 Miranda Res |  | Full height Turnstile | bar: 2022-02-07 to 2022-05-09
| DSLSC004 Miranda Res |  | container - tool | bar: 2022-02-07 to 2022-05-09
| DSLSC004 Miranda Res |  | container - rigging | bar: 2022-02-07 to 2022-05-09
| DSLSC004 Miranda Res |  | container - haz. goods | bar: 2022-02-07 to 2022-05-09
| DSLSC004 Miranda Res |  | Tally hut | bar: 2022-02-07 to 2022-05-09
| DSLSC004 Miranda Res |  | switchboard | bar: 2022-02-07 to 2022-05-09
| DSLSC004 Miranda Res |  | cage - 4 man | bar: 2022-02-07 to 2022-05-09
| DSLSC004 Miranda Res |  | cage - rescue | bar: 2022-02-07 to 2022-05-09
| DSLSC004 Miranda Res |  | cage - materials | bar: 2022-02-07 to 2022-05-09
| DSLSC004 Miranda Res |  | cage - open | bar: 2022-02-07 to 2022-05-09
| DSLSC004 Miranda Res |  | skip - 4m3 | bar: 2022-02-07 to 2022-05-09
DSLSC005 PS25 START:21/12/21 DURATION:28WKS
DSLSC005 PS25 | bar: 2021-12-06 to 2021-12-13; 2022-01-03 to 2022-07-25
DSLSC005 PS25 | bar: 2021-12-06 to 2021-12-13; 2022-01-03 to 2022-07-25
DSLSC005 PS25 | bar: 2021-12-06 to 2021-12-13; 2022-01-03 to 2022-07-25
DSLSC005 PS25 | bar: 2021-12-06 to 2021-12-13; 2022-01-03 to 2022-07-25
DSLSC005 PS25 | bar: 2021-12-06 to 2021-12-13; 2022-01-03 to 2022-07-25
DSLSC005 PS25 | bar: 2021-12-06 to 2021-12-13; 2022-01-03 to 2022-07-25
DSLSC005 PS25 | bar: 2021-12-06 to 2021-12-13; 2022-01-03 to 2022-07-25
DSLSC005 PS25 | bar: 2021-12-06 to 2021-12-13; 2022-01-03 to 2022-07-25
DSLSC005 PS25 | bar: 2021-12-06 to 2021-12-13; 2022-01-03 to 2022-07-25
DSLSC005 PS25 | bar: 2021-12-06 to 2021-12-13; 2022-01-03 to 2022-07-25
DSLSC005 PS25 | bar: 2021-12-06 to 2021-12-13; 2022-01-03 to 2022-07-25
DSLSC005 PS25 | bar: 2021-12-06 to 2021-12-13; 2022-01-03 to 2022-07-25
DSLSC005 PS25 | bar: 2021-12-06 to 2021-12-13; 2022-01-03 to 2022-07-25
DSLSC005 PS25 | bar: 2021-12-06 to 2021-12-13; 2022-01-03 to 2022-07-25
DSLSC005 PS25 | bar: 2021-12-06 to 2021-12-13; 2022-01-03 to 2022-07-25
DSLSC005 PS25 | bar: 2021-12-06 to 2021-12-13; 2022-01-03 to 2022-07-25
DSLSC005 PS25 | bar: 2021-12-06 to 2021-12-13; 2022-01-03 to 2022-07-25
DSLSC005 PS25 | bar: 2021-12-06 to 2021-12-13; 2022-01-03 to 2022-07-25
DSLSC005 PS25 | bar: 2021-12-06 to 2021-12-13; 2022-01-03 to 2022-07-25
DSLSC005 PS25 | bar: 2021-12-06 to 2021-12-13; 2022-01-03 to 2022-07-25
DSLSC005 PS25 | bar: 2021-12-06 to 2021-12-13; 2022-01-03 to 2022-07-25
DSLSC005 PS25 | bar: 2021-12-06 to 2021-12-13; 2022-01-03 to 2022-07-25
DSLSC005 PS25 | bar: 2021-12-06 to 2021-12-13; 2022-01-03 to 2022-07-25
DSCIN006 Haverstock START:21/09/22 DURATION:29WKS
| DSCIN006 Haverstock |  | crawler crane | bar: 2022-09-05 to 2022-12-12; 2023-01-02 to 2023-05-01
| DSCIN006 Haverstock |  | 38t digger - telescopic | bar: 2022-09-19 to 2022-11-07
| DSCIN006 Haverstock |  | UG digger (8t) | bar: 2022-09-05 to 2022-12-12; 2023-01-02 to 2023-05-01
| DSCIN006 Haverstock |  | Digger breaker (8t) | bar: 2022-09-05 to 2022-12-12; 2023-01-02 to 2023-05-01
| DSCIN006 Haverstock |  | digger drill attachment (8t) | bar: 2022-09-05 to 2022-12-12; 2023-01-02 to 2023-05-01
| DSCIN006 Haverstock |  | Digger attachement brush (8t) | bar: 2022-09-05 to 2022-12-12; 2023-01-02 to 2023-05-01
| DSCIN006 Haverstock |  | digger milling head (8t) | bar: 2022-09-05 to 2022-12-12; 2023-01-02 to 2023-05-01
| DSCIN006 Haverstock |  | Surface digger (14t) | bar: 2022-09-05 to 2022-12-12; 2023-01-02 to 2023-05-01
| DSCIN006 Haverstock |  | generator - backup - 300kVA | bar: 2022-09-05 to 2022-12-12; 2023-01-02 to 2023-05-01
| DSCIN006 Haverstock |  | ventilation fan | bar: 2022-09-05 to 2022-12-12; 2023-01-02 to 2023-05-01
| DSCIN006 Haverstock |  | Submersible pump | 2022-09-05: 2; 2022-09-12: 2; 2022-09-19: 2; 2022-09-26: 2; 2022-10-03: 2; 2022-10-10: 2; 2022-10-17: 2; 2022-10-24: 2; 2022-10-31: 2; 2022-11-07: 2; 2022-11-14: 2; 2022-11-21: 2; 2022-11-28: 2; 2022-12-05: 2; 2022-12-12: 2; 2023-01-02: 2; 2023-01-09: 2; 2023-01-16: 2; 2023-01-23: 2; 2023-01-30: 2; 2023-02-06: 2; 2023-02-13: 2; 2023-02-20: 2; 2023-02-27: 2; 2023-03-06: 2; 2023-03-13: 2; 2023-03-20: 2; 2023-03-27: 2; 2023-04-03: 2; 2023-04-10: 2; 2023-04-17: 2; 2023-04-24: 2; 2023-05-01: 2
| DSCIN006 Haverstock |  | gasguard | bar: 2022-09-05 to 2022-12-12; 2023-01-02 to 2023-05-01
| DSCIN006 Haverstock |  | Full height Turnstile | bar: 2022-09-05 to 2022-12-12; 2023-01-02 to 2023-05-01
| DSCIN006 Haverstock |  | container - tool | bar: 2022-09-05 to 2022-12-12; 2023-01-02 to 2023-05-01
| DSCIN006 Haverstock |  | container - rigging | bar: 2022-09-05 to 2022-12-12; 2023-01-02 to 2023-05-01
| DSCIN006 Haverstock |  | container - haz. goods | bar: 2022-09-05 to 2022-12-12; 2023-01-02 to 2023-05-01
| DSCIN006 Haverstock |  | Tally hut | bar: 2022-09-05 to 2022-12-12; 2023-01-02 to 2023-05-01
| DSCIN006 Haverstock |  | switchboard | bar: 2022-09-05 to 2022-12-12; 2023-01-02 to 2023-05-01
| DSCIN006 Haverstock |  | cage - 4 man | bar: 2022-09-05 to 2022-12-12; 2023-01-02 to 2023-05-01
| DSCIN006 Haverstock |  | cage - rescue | bar: 2022-09-05 to 2022-12-12; 2023-01-02 to 2023-05-01
| DSCIN006 Haverstock |  | cage - materials | bar: 2022-09-05 to 2022-12-12; 2023-01-02 to 2023-05-01
| DSCIN006 Haverstock |  | cage - open | bar: 2022-09-05 to 2022-12-12; 2023-01-02 to 2023-05-01
| DSCIN006 Haverstock |  | skip - 3m3 | bar: 2022-09-05 to 2022-12-12; 2023-01-02 to 2023-05-01
| DSCIN006 Haverstock |  | Putzmeister S5 Ev Grout Pump | bar: 2022-09-05 to 2022-12-12; 2023-01-02 to 2023-05-01
| DSCIN006 Haverstock |  | compressor - 200CFM | bar: 2022-09-05 to 2022-12-12; 2023-01-02 to 2023-05-01
DSCIN008 Mt Albert START: 7/7/2022 DURATION: 21 WKS
| DSCIN008 Mt Albert |  | crawler crane | bar: 2022-06-20 to 2022-12-05
| DSCIN008 Mt Albert |  | UG digger (8t) | bar: 2022-06-20 to 2022-12-05
| DSCIN008 Mt Albert |  | Digger breaker (8t) | bar: 2022-06-20 to 2022-12-05
| DSCIN008 Mt Albert |  | digger drill attachment (8t) | bar: 2022-06-20 to 2022-12-05
| DSCIN008 Mt Albert |  | Digger attachement brush (8t) | bar: 2022-06-20 to 2022-12-05
| DSCIN008 Mt Albert |  | digger milling head (8t) | bar: 2022-06-20 to 2022-12-05
| DSCIN008 Mt Albert |  | Surface digger (14t) | bar: 2022-06-20 to 2022-12-05
| DSCIN008 Mt Albert |  | generator - backup - 300kVA | bar: 2022-06-20 to 2022-12-05
| DSCIN008 Mt Albert |  | ventilation fan | bar: 2022-06-20 to 2022-12-05
| DSCIN008 Mt Albert |  | Submersible pump | 2022-06-20: 2; 2022-06-27: 2; 2022-07-04: 2; 2022-07-11: 2; 2022-07-18: 2; 2022-07-25: 2; 2022-08-01: 2; 2022-08-08: 2; 2022-08-15: 2; 2022-08-22: 2; 2022-08-29: 2; 2022-09-05: 2; 2022-09-12: 2; 2022-09-19: 2; 2022-09-26: 2; 2022-10-03: 2; 2022-10-10: 2; 2022-10-17: 2; 2022-10-24: 2; 2022-10-31: 2; 2022-11-07: 2; 2022-11-14: 2; 2022-11-21: 2; 2022-11-28: 2; 2022-12-05: 2
| DSCIN008 Mt Albert |  | gasguard | bar: 2022-06-20 to 2022-12-05
| DSCIN008 Mt Albert |  | Full height Turnstile | bar: 2022-06-20 to 2022-12-05
| DSCIN008 Mt Albert |  | container - tool | bar: 2022-06-20 to 2022-12-05
| DSCIN008 Mt Albert |  | container - rigging | bar: 2022-06-20 to 2022-12-05
| DSCIN008 Mt Albert |  | container - haz. goods | bar: 2022-06-20 to 2022-12-05
| DSCIN008 Mt Albert |  | Tally hut | bar: 2022-06-20 to 2022-12-05
| DSCIN008 Mt Albert |  | switchboard | bar: 2022-06-20 to 2022-12-05
| DSCIN008 Mt Albert |  | cage - 4 man | bar: 2022-06-20 to 2022-12-05
| DSCIN008 Mt Albert |  | cage - rescue | bar: 2022-06-20 to 2022-12-05
| DSCIN008 Mt Albert |  | cage - materials | bar: 2022-06-20 to 2022-12-05
| DSCIN008 Mt Albert |  | cage - open | bar: 2022-06-20 to 2022-12-05
| DSCIN008 Mt Albert |  | skip - 3m3 | bar: 2022-06-20 to 2022-12-05
| DSCIN008 Mt Albert |  | Putzmeister S5 Ev Grout Pump | bar: 2022-06-20 to 2022-12-05
| DSCIN008 Mt Albert |  | compressor - 200CFM | bar: 2022-06-20 to 2022-12-05
DSLSB001 Norgrove START: 16/01/2023 DURATION: 20WKS
| DSLSB001 Norgrove Ave |  | crawler crane | bar: 2023-01-02 to 2023-06-12
| DSLSB001 Norgrove Ave |  | 38t digger - telescopic | bar: 2023-01-02 to 2023-06-12
| DSLSB001 Norgrove Ave |  | UG digger (5.5t) | bar: 2023-01-02 to 2023-06-12
| DSLSB001 Norgrove Ave |  | Digger breaker (5.5t) | bar: 2023-01-02 to 2023-06-12
| DSLSB001 Norgrove Ave |  | digger drill attachment (5.5t) | bar: 2023-01-02 to 2023-06-12
| DSLSB001 Norgrove Ave |  | Digger attachement brush (5.5t) | bar: 2023-01-02 to 2023-06-12
| DSLSB001 Norgrove Ave |  | digger milling head (5.5t) | bar: 2023-01-02 to 2023-06-12
| DSLSB001 Norgrove Ave |  | Surface digger (14t) | bar: 2023-01-02 to 2023-06-12
| DSLSB001 Norgrove Ave |  | generator - backup - 300kVA | bar: 2023-01-02 to 2023-06-12
| DSLSB001 Norgrove Ave |  | ventilation fan | bar: 2023-01-02 to 2023-06-12
| DSLSB001 Norgrove Ave |  | Submersible pump | 2023-01-02: 2; 2023-01-09: 2; 2023-01-16: 2; 2023-01-23: 2; 2023-01-30: 2; 2023-02-06: 2; 2023-02-13: 2; 2023-02-20: 2; 2023-02-27: 2; 2023-03-06: 2; 2023-03-13: 2; 2023-03-20: 2; 2023-03-27: 2; 2023-04-03: 2; 2023-04-10: 2; 2023-04-17: 2; 2023-04-24: 2; 2023-05-01: 2; 2023-05-08: 2; 2023-05-15: 2; 2023-05-22: 2; 2023-05-29: 2; 2023-06-05: 2; 2023-06-12: 2
| DSLSB001 Norgrove Ave |  | gasguard | bar: 2023-01-02 to 2023-06-12
| DSLSB001 Norgrove Ave |  | Full height Turnstile | bar: 2023-01-02 to 2023-06-12
| DSLSB001 Norgrove Ave |  | container - tool | bar: 2023-01-02 to 2023-06-12
| DSLSB001 Norgrove Ave |  | container - rigging | bar: 2023-01-02 to 2023-06-12
| DSLSB001 Norgrove Ave |  | container - haz. goods | bar: 2023-01-02 to 2023-06-12
| DSLSB001 Norgrove Ave |  | Tally hut | bar: 2023-01-02 to 2023-06-12
| DSLSB001 Norgrove Ave |  | switchboard | bar: 2023-01-02 to 2023-06-12
| DSLSB001 Norgrove Ave |  | cage - 4 man | bar: 2023-01-02 to 2023-06-12
| DSLSB001 Norgrove Ave |  | cage - rescue | bar: 2023-01-02 to 2023-06-12
| DSLSB001 Norgrove Ave |  | cage - materials | bar: 2023-01-02 to 2023-06-12
| DSLSB001 Norgrove Ave |  | cage - open | bar: 2023-01-02 to 2023-06-12
| DSLSB001 Norgrove Ave |  | skip - 3m3 | bar: 2023-01-02 to 2023-06-12
| DSLSB001 Norgrove Ave |  | Putzmeister S5 Ev Grout Pump | bar: 2023-01-02 to 2023-06-12
| DSLSB001 Norgrove Ave |  | compressor - 200CFM | bar: 2023-01-02 to 2023-06-12
DSLSB002 Rawalpindi START: 19/08/022 DURATION: 24WKS
| DSLSB002 Rawalpindi Res |  | crawler crane | bar: 2022-08-01 to 2022-12-12; 2023-01-02 to 2023-02-20
| DSLSB002 Rawalpindi Res |  | 38t digger - telescopic | bar: 2022-08-01 to 2022-10-03
| DSLSB002 Rawalpindi Res |  | UG digger (8t) | bar: 2022-08-01 to 2022-12-12; 2023-01-02 to 2023-02-20
| DSLSB002 Rawalpindi Res |  | Digger breaker (8t) | bar: 2022-08-01 to 2022-12-12; 2023-01-02 to 2023-02-20
| DSLSB002 Rawalpindi Res |  | digger drill attachment (8t) | bar: 2022-08-01 to 2022-12-12; 2023-01-02 to 2023-02-20
| DSLSB002 Rawalpindi Res |  | Digger attachement brush (8t) | bar: 2022-08-01 to 2022-12-12; 2023-01-02 to 2023-02-20
| DSLSB002 Rawalpindi Res |  | digger milling head (8t) | bar: 2022-08-01 to 2022-12-12; 2023-01-02 to 2023-02-20
| DSLSB002 Rawalpindi Res |  | Surface digger (14t) | bar: 2022-08-01 to 2022-12-12; 2023-01-02 to 2023-02-20
| DSLSB002 Rawalpindi Res |  | generator - backup - 300kVA | bar: 2022-08-01 to 2022-12-12; 2023-01-02 to 2023-02-20
| DSLSB002 Rawalpindi Res |  | ventilation fan | bar: 2022-08-01 to 2022-12-12; 2023-01-02 to 2023-02-20
| DSLSB002 Rawalpindi Res |  | Submersible pump | 2022-08-01: 2; 2022-08-08: 2; 2022-08-15: 2; 2022-08-22: 2; 2022-08-29: 2; 2022-09-05: 2; 2022-09-12: 2; 2022-09-19: 2; 2022-09-26: 2; 2022-10-03: 2; 2022-10-10: 2; 2022-10-17: 2; 2022-10-24: 2; 2022-10-31: 2; 2022-11-07: 2; 2022-11-14: 2; 2022-11-21: 2; 2022-11-28: 2; 2022-12-05: 2; 2022-12-12: 2; 2023-01-02: 2; 2023-01-09: 2; 2023-01-16: 2; 2023-01-23: 2; 2023-01-30: 2; 2023-02-06: 2; 2023-02-13: 2; 2023-02-20: 2
| DSLSB002 Rawalpindi Res |  | gasguard | bar: 2022-08-01 to 2022-12-12; 2023-01-02 to 2023-02-20
| DSLSB002 Rawalpindi Res |  | Full height Turnstile | bar: 2022-08-01 to 2022-12-12; 2023-01-02 to 2023-02-20
| DSLSB002 Rawalpindi Res |  | container - tool | bar: 2022-08-01 to 2022-12-12; 2023-01-02 to 2023-02-20
| DSLSB002 Rawalpindi Res |  | container - rigging | bar: 2022-08-01 to 2022-12-12; 2023-01-02 to 2023-02-20
| DSLSB002 Rawalpindi Res |  | container - haz. goods | bar: 2022-08-01 to 2022-12-12; 2023-01-02 to 2023-02-20
| DSLSB002 Rawalpindi Res |  | Tally hut | bar: 2022-08-01 to 2022-12-12; 2023-01-02 to 2023-02-20
| DSLSB002 Rawalpindi Res |  | switchboard | bar: 2022-08-01 to 2022-12-12; 2023-01-02 to 2023-02-20
| DSLSB002 Rawalpindi Res |  | cage - 4 man | bar: 2022-08-01 to 2022-12-12; 2023-01-02 to 2023-02-20
| DSLSB002 Rawalpindi Res |  | cage - rescue | bar: 2022-08-01 to 2022-12-12; 2023-01-02 to 2023-02-20
| DSLSB002 Rawalpindi Res |  | cage - materials | bar: 2022-08-01 to 2022-12-12; 2023-01-02 to 2023-02-20
| DSLSB002 Rawalpindi Res |  | cage - open | bar: 2022-08-01 to 2022-12-12; 2023-01-02 to 2023-02-20
| DSLSB002 Rawalpindi Res |  | skip - 3m3 | bar: 2022-08-01 to 2022-12-12; 2023-01-02 to 2023-02-20
| DSLSB002 Rawalpindi Res |  | Putzmeister S5 Ev Grout Pump | bar: 2022-08-01 to 2022-12-12; 2023-01-02 to 2023-02-20
| DSLSB002 Rawalpindi Res |  | compressor - 200CFM | bar: 2022-08-01 to 2022-12-12; 2023-01-02 to 2023-02-20
LYON AVE START: 25/01/2023 DURATON:33 WKS
| DSCIN007 Lyon Ave |  | crawler crane | bar: 2023-01-09 to 2023-09-18
| DSCIN007 Lyon Ave | 5.5t as backup | UG digger (8t) | bar: 2023-01-09 to 2023-09-18
| DSCIN007 Lyon Ave |  | Digger breaker (8t) | bar: 2023-01-09 to 2023-09-18
| DSCIN007 Lyon Ave |  | digger drill attachment (8t) | bar: 2023-01-09 to 2023-09-18
| DSCIN007 Lyon Ave |  | Digger attachement brush (8t) | bar: 2023-01-09 to 2023-09-18
| DSCIN007 Lyon Ave |  | digger milling head (8t) | bar: 2023-01-09 to 2023-09-18
| DSCIN007 Lyon Ave |  | Surface digger (14t) | bar: 2023-01-09 to 2023-09-18
| DSCIN007 Lyon Ave |  | generator - backup - 300kVA | bar: 2023-01-09 to 2023-09-18
| DSCIN007 Lyon Ave |  | ventilation fan | bar: 2023-01-09 to 2023-09-18
| DSCIN007 Lyon Ave |  | Submersible pump | 2023-01-09: 2; 2023-01-16: 2; 2023-01-23: 2; 2023-01-30: 2; 2023-02-06: 2; 2023-02-13: 2; 2023-02-20: 2; 2023-02-27: 2; 2023-03-06: 2; 2023-03-13: 2; 2023-03-20: 2; 2023-03-27: 2; 2023-04-03: 2; 2023-04-10: 2; 2023-04-17: 2; 2023-04-24: 2; 2023-05-01: 2; 2023-05-08: 2; 2023-05-15: 2; 2023-05-22: 2; 2023-05-29: 2; 2023-06-05: 2; 2023-06-12: 2; 2023-06-19: 2; 2023-06-26: 2; 2023-07-03: 2; 2023-07-10: 2; 2023-07-17: 2; 2023-07-24: 2; 2023-07-31: 2; 2023-08-07: 2; 2023-08-14: 2; 2023-08-21: 2; 2023-08-28: 2; 2023-09-04: 2; 2023-09-11: 2; 2023-09-18: 2
| DSCIN007 Lyon Ave |  | gasguard | bar: 2023-01-09 to 2023-09-18
| DSCIN007 Lyon Ave |  | Full height Turnstile | bar: 2023-01-09 to 2023-09-18
| DSCIN007 Lyon Ave |  | container - tool | bar: 2023-01-09 to 2023-09-18
| DSCIN007 Lyon Ave |  | container - rigging | bar: 2023-01-09 to 2023-09-18
| DSCIN007 Lyon Ave |  | container - haz. goods | bar: 2023-01-09 to 2023-09-18
| DSCIN007 Lyon Ave |  | Tally hut | bar: 2023-01-09 to 2023-09-18
| DSCIN007 Lyon Ave |  | switchboard | bar: 2023-01-09 to 2023-09-18
| DSCIN007 Lyon Ave |  | cage - 4 man | bar: 2023-01-09 to 2023-09-18
| DSCIN007 Lyon Ave |  | cage - rescue | bar: 2023-01-09 to 2023-09-18
| DSCIN007 Lyon Ave |  | cage - materials | bar: 2023-01-09 to 2023-09-18
| DSCIN007 Lyon Ave |  | cage - open | bar: 2023-01-09 to 2023-09-18
| DSCIN007 Lyon Ave |  | skip - 3m3
| DSCIN007 Lyon Ave |  | Putzmeister S5 Ev Grout Pump
| DSCIN007 Lyon Ave |  | compressor - 200CFM
| DSCIN007 Lyon Ave |  | shotcrete - Aliva 272
WESTERN SPRINGS START: 1/6/23 DURATION: 26WKS
| DSCIN009 Western Springs |  | crawler crane | bar: 2023-05-15 to 2023-12-04
| DSCIN009 Western Springs |  | UG digger (23t) | bar: 2023-05-15 to 2023-12-04
| DSCIN009 Western Springs |  | Digger breaker (23t) | bar: 2023-05-15 to 2023-12-04
| DSCIN009 Western Springs |  | UG digger (14t) | bar: 2023-05-15 to 2023-12-04
| DSCIN009 Western Springs |  | digger drill attachment (14t) | bar: 2023-05-15 to 2023-12-04
| DSCIN009 Western Springs |  | Digger attachement brush (14t) | bar: 2023-05-15 to 2023-12-04
| DSCIN009 Western Springs |  | digger milling head (14t) | bar: 2023-05-15 to 2023-12-04
| DSCIN009 Western Springs |  | digger breaker (14t) | bar: 2023-05-15 to 2023-12-04
| DSCIN009 Western Springs |  | Surface digger (14t) | bar: 2023-05-15 to 2023-12-04
| DSCIN009 Western Springs |  | generator - backup - 300kVA | bar: 2023-05-15 to 2023-12-04
| DSCIN009 Western Springs |  | ventilation fan | bar: 2023-05-15 to 2023-12-04
| DSCIN009 Western Springs |  | Submersible pump | 2023-05-15: 2; 2023-05-22: 2; 2023-05-29: 2; 2023-06-05: 2; 2023-06-12: 2; 2023-06-19: 2; 2023-06-26: 2; 2023-07-03: 2; 2023-07-10: 2; 2023-07-17: 2; 2023-07-24: 2; 2023-07-31: 2; 2023-08-07: 2; 2023-08-14: 2; 2023-08-21: 2; 2023-08-28: 2; 2023-09-04: 2; 2023-09-11: 2; 2023-09-18: 2; 2023-09-25: 2; 2023-10-02: 2; 2023-10-09: 2; 2023-10-16: 2; 2023-10-23: 2; 2023-10-30: 2; 2023-11-06: 2; 2023-11-13: 2; 2023-11-20: 2; 2023-11-27: 2; 2023-12-04: 2
| DSCIN009 Western Springs |  | gasguard | bar: 2023-05-15 to 2023-12-04
| DSCIN009 Western Springs |  | Full height Turnstile | bar: 2023-05-15 to 2023-12-04
| DSCIN009 Western Springs |  | container - tool | bar: 2023-05-15 to 2023-12-04
| DSCIN009 Western Springs |  | container - rigging | bar: 2023-05-15 to 2023-12-04
| DSCIN009 Western Springs |  | container - haz. goods | bar: 2023-05-15 to 2023-12-04
| DSCIN009 Western Springs |  | Tally hut | bar: 2023-05-15 to 2023-12-04
| DSCIN009 Western Springs |  | switchboard | bar: 2023-05-15 to 2023-12-04
| DSCIN009 Western Springs |  | cage - 4 man | bar: 2023-05-15 to 2023-12-04
| DSCIN009 Western Springs |  | cage - rescue | bar: 2023-05-15 to 2023-12-04
| DSCIN009 Western Springs |  | cage - materials | bar: 2023-05-15 to 2023-12-04
| DSCIN009 Western Springs |  | cage - open | bar: 2023-05-15 to 2023-12-04
| DSCIN009 Western Springs |  | skip - 4m3 | bar: 2023-05-15 to 2023-12-04
| DSCIN009 Western Springs |  | Putzmeister S5 Ev Grout Pump | bar: 2023-05-15 to 2023-12-04
| DSCIN009 Western Springs |  | compressor - 200CFM | bar: 2023-05-15 to 2023-12-04
Tawarki street - diametre tbc
Note on D62: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 14t excavator to be trialled in shaft A - 8t as back up
Note on D80: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4m3 skip required if 8t machine in hole

## Diggers
DIGGER SELECTION
SHAFT IDENTIFICATION | DSCIN004A May Road A | DSCIN004B May Road B | DSCIN006 Haverstock Road | DSCIN007 Lyon Avenue | DSCIN008 Mt Albert War Memorial Reserve | DSCIN009 Western Springs | DSLSB001 Norgrove Avenue | DSLSB002 Rawalpindi Reserve | DSLSC001 Haycock Avenue | DSLSC002 Dundale Avenue | DSLSC004 Miranda Reserve | DSLSC005 PS25
CORRIDOR | Main Tunnel / LSC | Main Tunnel | Main Tunnel | Main Tunnel | Main Tunnel /Link Sewer B | Main Tunnel | Link Sewer B | Link Sewer B | Link Sewer C | Link Sewer C | Link Sewer C | Link Sewer C
Temporary Works ID upper | 9.9 | 12.4 | 9.4 | 7.5 | 8 | 13.4 | 7.2 | 9.3 | 8 | 11.3 | 12.9 x 9.3
elliptical
Temporary Works ID lower | 8.9 | 12.4 | 8.4 | 8 | 9 | 12.2 | 6 | 8.3 | 7.7 | 11.5 | 12.9 x 9.3
elliptical
Overall Shaft Depth (mBGL) | 71.3 | 72.9 | 48 | 45 | 37.7 | 30.1 | 29.7 | 28.2 | 29.1 | 23.6 | 15.6 | 12
Temporary Case usage (Launch/Drive through/Retrieval) | Main Tunnel Drive Through Shaft, LSC launch shaft | Main tunnel section 2 working shaft | Main tunnel drive through shaft | Main tunnel drive through shaft | LSB and Adit launch Shaft | Drive Through Shaft | Double Retrieval Shaft | Launch Shaft | Double Retrieval Shaft | Launch Shaft (bi-direction) | Launch Shaft (bi-direction) | Retrieval Shaft
Digger Requirements
UG digger | 8t | 14t | 8t | 6t | 8t | 14t | 6t | 8t | 6t | 14t | 14t | 3.5t
Surface digger (muck bay) | 14t | 14t | 14t | 14t | 14t | 14t | 14t | 14t | 14t | 14t | 14t | 14t

## 3.5t range
3.5t digger range
Manufacturer / Model | Airman AX33U | Hyundai R35Z-9 | Takeuchi TB235-2
Dimensions
operating weight (kg) | 3230 | 3840 | 3465
overall width (mm) | 1550 | 1740 | 1580
tumbler length (mm) | 1660 | 1700
Overall length (mm) | 4450 | 4790 | 4900
Min front swing radius (mm) | 1970 | 2350 | 1660
height (mm) | 2480 | 2500 | 2005
Engine / Hydraulic
Rated power (kW) | 21.2 @ 2400 rpm | 24.4 @ 2200 rpm | 18.2 @ 2400 rpm
Main pump oil flow (l/min) | 2x 38.4 | 2 x 37.4 | 60
Pilot pump (l/min) |  | 9.9
Digging Power
Bucket dig force m(kN) | 27.2 | 30.7 | 38.9
Boom cylinder (mm) | 80 x 579 | 85 x 540 | -
Arm cylinder (mm) | 70 x 546 | 80 x 585 | -
Bucket cylinder (mm) | 65 x 435 | 70 x 510 | -
Blade cylinder (mm) | 85 x 135 | 95 x 152 | -
Boom swing cylinder (mm) | 85 x 525 | 80 x 400 | -
Test comments

## 6t range
6t digger range
Manufacturer / Model | Airman AX55U | Hyundai R60CR-9A | Mecalac 6MCR | Takeuchi TB260 | Komatsu PC45MR-5 | Cat 305E2 CR | Hyundai R55CR-9
Dimensions
operating weight (kg) | 5210 | 5900 | 5700 | 5735 | 4980 | 5140
overall width (mm) | 2000 | 2000 | 2030 | 2000 | 1960 | 1980
tumbler length (mm) | 2000 | 1990 | 1880 | 2050 | 2000 | -
Overall length (mm) | 5475 | 5600 | 2831 | 5500 | 5220 | 5180
Min front swing radius (mm) | 2300 | 2470 | 2876 | 2420 | 2290 | 2350
height (mm) | 2530 | 2550 | 2751 | 2575 | 2590 | 2550
Engine / Hydraulic
Rated power (kW) | 28.2 @ 2400rpm | 48kW @ 2200rpm | 55kW @ 2200rpm | 35.5kW @ 2400rpm | 29.1 @ 2400rpm | 60 @ 2200rpm
Main pump oil flow (l/min) | 1 x 120 | 2 x 55 | 2 x 100 | 102.2 | 153.3 | 150
Pilot pump (l/min) | 12 | 6.9
Digging Power
Bucket dig force m(kN) | 36.9 | 40.9 | 40.5 | 43.2 | 33.9 | 44.7
Boom cylinder (mm) | 90 x 699 | 110 x 715 | - | - | 90 x 691 | -
Arm cylinder (mm) | 80 x 698 | 85 x 840 | - | - | 80 x 649 | -
Bucket cylinder (mm) | 70 x 551 | 80 x 660 | - | - | 70 x 580 | -
Blade cylinder (mm) | 105 x 140 | 110 x 244 | - | - | 110 x 140 | -
Boom swing cylinder (mm) | 90 x 666 | 95 x 519 | - | - | 90 x 630 | -
Test comments | Mechanical team adjusted hydraulics. Performance improved. |  | worst | Not tested |  | Best performance per the operator | Similar to Airman AX55 after its modifications
Preference | 2 | not tested | 3 | - | worst | 1 | 2
Excavator Price | 87000 | 73000 | 134000 | 86990 | 90604 | 88290 | 69000
Trenching Bucket | TBA | 1600 | INC | TBA | TBA | 1205 | 1800
Mine spec | 44450 | 39120 | 3000 | 34500 | 21000 | 48030 | 34500
Total Price | 131450 | 113720 | 137000 | 121490 | 111604 | 137525 | 105300
Lead time | [5 empty] | 2 months

## 8t range
8t digger range
Manufacturer / Model | Hyundai R80CR-9A | Mecalac 8MCR | Takeuchi TB285 | Komatsu PC78UU-10 | Cat 306CR | Cat 307CR
Dimensions
operating weight (kg) | 8750 | 7200 | 8390 | 7960 | 7140 | 8120
overall width (mm) | 2300 | 2030 | 2200 | 2320 | 1980 | 2200
tumbler length (mm) | 2200 | 2095 | 2210 | 2235 | -
Overall length (mm) | 6170 | 3088 | 6945 | 6060 | 5975 | 6230
Min front swing radius (mm) | 2500 | 2888 | 2495 | 1200 | -
height (mm) | 2640 | 2900 | 2565 | 2730 | 2545
Engine / Hydraulic
Rated power (kW) | 49.9 @ 2400 rpm | 55.4 @2300 rpm | 51.6 @ 2000 rpm | 50.7 @ - | 43.2 @ -
Main pump oil flow (l/min) | 2 x 68.4 | 1 x 56 | 100 | 160 | 151
Pilot pump (l/min)
Digging Power
Bucket dig force m(kN) | 42.1 | 51 | 59.1 | 61.3 | 51.5 | 54.6
Boom cylinder (mm) | 115 x 850 mm | - | - | 120 x 1015 | -
Arm cylinder (mm) | 100 x 870 mm | - | - | 110 x 715 | -
Bucket cylinder (mm) | 85 x 685 mm | - | - | 90 x 710 | -
Blade cylinder (mm) | 130 x 152 mm | - | - | 130 x 130 | -
Boom swing cylinder (mm) | 110 x 744 mm | - | - | 110 x 350 | -
Preference
Excavator Price
Trenching Bucket
Mine spec
Comments |  |  |  | Similar size to the current Hyundai R80. Best break-out power. Best hydraulic flow rates (tooling). Good operating weight.

## 14t range
14t digger range | [6 empty] | 23t
Manufacturer / Model | CAT 313 | CAT 315 | DOOSAN DX 140 | Hyundai HX145CR | Hyundai R140LC-9 | Komatsu PC 138
Dimensions
operating weight (kg) | 13800 | 15400 | 14870 | 14660 | 13790 | 13480 | 23800
overall width (mm) | 2490 | 2490 | 2590 | 2500 | 2700 | 2490 | 3000
tumbler length (mm) | 3040 | 3040 | 3035 | 2910 | 3750 | 2880 | 4400
Overall length (mm) | 8050 | 8090 | 7640 | 7250 | 7810 | 7260 | 9040
Min front swing radius (mm) | 2570 | 2570 | 2625 | 2330 | 2620 | 1980
height (mm) | 2810 | 2810 | 2785 | 2935 | 2820 | 2850
Engine / Hydraulic
Rated power (kW) | 82kW @ | 82kW@ | 86 kW @ 2000 | 97 kW @ 2000 | 89 kW @ 2000 | 68.4 kW @ 2200
Main pump oil flow (l/min) | 247 ( total) | 276 (total) | 2 x 114 | 2 x 120 | 2x123.5 | 241.5 (total)
Pilot pump (l/min)
Digging Power
Bucket dig force m(kN) | 98.67 | 98.67 | 107.87 | 101.8 | 102 | 93.2 | 152
Boom cylinder (mm) | - | - | 110 x 1108 | - | - | 105 x 1055
Arm cylinder (mm) | - | - | 115 x 1108 | - | - | 110 x 1175
Bucket cylinder (mm) | - | - | 100 x 900 | - | - | 95 x 885
Blade cylinder (mm) | - | - | - | - | - | -
Boom swing cylinder (mm) | - | - | - | - | - | -
Preference | - | - | 2 | 1 | 3
Excavator Price |  |  |  | 186000 | 156000
Trenching Bucket
Mine spec
Comments | too long | too long |  | - This is a newer model to the current UG 14t digger, allowing easier maintenance.
- Need short boom, allow ~$20k.

## Craneage
SHAFTS CRANEAGE REQUIREMENTS (regular lifts) |  |  |  |  | Completed by Plant Manager (embed lifting charts) | Approved by Construction Manager
Location / Works | Max Lift Description | Max Lift | Max Radius | Max Depth | Plant requirement
|  | (excluding block, rope, rigging, etc.) | (m) | (m)
Dundale | 14t digger | 17t
PS25 | 3.5t digger | To be discussed
PS23 | N/A
Keith Hay Park | N/A
May Rd A | 8t digger | 8.5t
Haycock | 6t digger | 6t
Whitney | 6t digger | 6t
Miranda | 14t digger | 17t
May Rd B | 23t digger | 28t
Walmsley | N/A
Haverstock | 8t digger
Lyon | 6t digger
Mt Albert | 8t digger
Western Springs | 14t digger | 17t
Norgrove | 6t digger
Rawalpindi | 8t digger